## Sheet1
SauceDemo – Test Execution Summary Report
Execution summary derived from the supplied 87 test cases
Metric | Result
Total test cases provided | 87
Clearly passed based on supplied Actual Results | 54
Open / failed observations | 30
Observation requiring classification | 2
Primary risk area | problem_user product, cart and sorting behavior
Other risk areas | empty-cart checkout; error_user sorting/cart; visual_user images/UI
Release recommendation | Not fully ready until High-priority product/cart defects are investigated and retested.
Data quality note | Some cases contain duplicated IDs/scenarios, typos, malformed URLs and inconsistent usernames/steps; cleanup is recommended before final submission.

## Category Summary
Category | Result | Risk
Authentication | Baseline valid login, invalid login and locked-out behavior passed. | Low
Products | Six products displayed; product-specific defects observed. | Medium/High
Cart | Basic add/remove passed; special-user Add to Cart failures observed. | High
Sorting | Passed for baseline users; failed for problem/error users. | High
Checkout | Valid checkout/purchase passed; empty-cart validation open. | Medium
UI | Visual/image and checkout alignment defects observed. | Medium